## Executive_Summary
Category | Metric | Value | Target | Status
Overall Performance | Total Projects | 17 | N/A | Info
Overall Performance | Completed Projects | 14 | N/A | Info
Overall Performance | Average Duration (days) | 165.0 | ≤100 | Over Target
NIH Compliance | IRB Compliance Rate (%) | 11.8 | ≥80 | Needs Improvement
NIH Compliance | DUA Compliance Rate (%) | 5.9 | ≥80 | Needs Improvement
Risk Assessment | High-Risk Projects | 9 (52.9%) | <10% | Elevated

## Stage_Analysis
stage | column | count | mean | median | std | min | max | benchmark | exceeds_count | exceeds_pct | severity
NOA to Initial Consult | days_noa_to_consult | 17 | 74 | 34 | 107.23 | 14 | 353 | 30 | 9 | 52.94 | 2.47
Intake to Request Submission | days_intake_to_submit | 17 | 21.71 | 10 | 27.34 | 0 | 92 | 14 | 5 | 29.41 | 1.55
Submission to Finalization | days_submit_to_finalize | 15 | 60.53 | 52 | 45.4 | 19 | 183 | 30 | 9 | 60 | 2.02
IRB Process | days_irb | 16 | 120 | 136.5 | 46.26 | 20 | 178 | 60 | 14 | 87.5 | 2
DUA Process | days_dua | 15 | 154.67 | 153 | 40.67 | 88 | 224 | 90 | 14 | 93.33 | 1.72
Total Process (NOA to Access) | days_total_process | 15 | 165 | 169 | 34.72 | 112 | 225 | 100 | 15 | 100 | 1.65

## Program_Performance
| days_total_process | [5 empty] | days_irb | days_dua | irb_on_target | dua_on_target | meets_all_targets | is_completed
| count | mean | median | std | min | max | mean | mean | mean | mean | mean | sum
Program
CDP | 2 | 198 | 198 | 28.3 | 178 | 218 | 81.5 | 190.5 | 0.3 | 0 | 0 | 2
CLINAQ Cohort 1 | 3 | 158.3 | 164 | 14.4 | 142 | 169 | 146.5 | 153 | 0 | 0 | 0 | 3
Hub Pilot Program | 1 | 199 | 199 |  | 199 | 199 | 165 | 199 | 0 | 0 | 0 | 1
PAIR | 1 | 143 | 143 |  | 143 | 143 | 101 | 120 | 0 | 0 | 0 | 1
Research Fellowship Cohort 3 | 8 | 157.8 | 155.5 | 40.2 | 112 | 225 | 113.1 | 145.1 | 0.1 | 0.1 | 0 | 7

## Risk_Assessment
Name | Program | days_total_process | days_irb | days_dua | risk_score | risk_level | risk_factors
Eva Sterling/ Xinyan Zhang | Hub Pilot Program | 199 | 165 | 199 | 8 | High | Late initial consult (58d); IRB delay (165d); DUA delay (199d); Critical total delay (199d)
Howard Prioleau | Research Fellowship Cohort 3 | 225 | 178 | 224 | 7 | High | IRB delay (178d); DUA delay (224d); Critical total delay (225d)
Lucretia Williams | Research Fellowship Cohort 3 | 189 | 130 | 188 | 7 | High | IRB delay (130d); DUA delay (188d); Critical total delay (189d)
Ying Yin/Sean Vasaitis | CDP | 218 | 20 | 211 | 7 | High | Late initial consult (353d); Late request submission (92d); DUA delay (211d); Critical total delay (218d)
Korin Reid | Research Fellowship Cohort 3 | 174 | 160 | 131 | 6 | High | Late initial consult (35d); Late request submission (21d); IRB delay (160d); DUA delay (131d)
Yanmin Gong | CDP | 178 | 143 | 170 | 6 | High | Late initial consult (353d); Late request submission (72d); IRB delay (143d); DUA delay (170d)
Uduak George | PAIR | 143 | 101 | 120 | 5 | High | Late initial consult (72d); IRB delay (101d); DUA delay (120d)
Asha Imanuelle | CLINAQ Cohort 1 | 164 | 150 | 153 | 5 | High | Late initial consult (34d); IRB delay (150d); DUA delay (153d)
Ling Zhang | Research Fellowship Cohort 3 | 137 | 102 | 131 | 5 | High | Late initial consult (39d); IRB delay (102d); DUA delay (131d)
Alexandra Kakadiaris | Research Fellowship Cohort 3 | 119 | 74 | 98 | 4 | Medium | IRB delay (74d); DUA delay (98d)
Candice Adams-Mitchell | CLINAQ Cohort 1 | 142 | 141 | 135 | 4 | Medium | IRB delay (141d); DUA delay (135d)
Andrew Nguyen | Research Fellowship Cohort 3 | 180 | 142 | 175 | 4 | Medium | IRB delay (142d); DUA delay (175d)
Sohail Vaghari | CLINAQ Cohort 1 | 169 | 132 | 171 | 4 | Medium | IRB delay (132d); DUA delay (171d)
Adebola Sulaiman | CLINAQ Cohort 1 |  | 163 |  | 3 | Medium | Late request submission (35d); IRB delay (163d)
Pegah Ahadian | Research Fellowship Cohort 3 | 112 | 76 | 88 | 3 | Medium | Late initial consult (40d); IRB delay (76d)
Xuan Wang | Research Fellowship Cohort 3 | 126 | 43 | 126 | 2 | Low | DUA delay (126d)
Debi Alexander | CDP |  |  |  | 2 | Low | Late initial consult (99d); Late request submission (62d)

## Project_Details
Name | Program | NOA | Intake Consult | # of days to consult from NOA | Data Request Submitted | # of days to submit request from Intake | Data Consult (if any) | Data Request Finalized | # of days to finalize request from submission | IRB Submitted* | IRB Determination shared with AADB | # of days for IRB (NIH Target=60) | DUA information shared | # of days to share DUA information from Intake | DUA Draft Sent | FE DUA | # of days for DUA (NIH Target=90) | Data Access Provided | # of days to Data Access from NOA | Data Access Confirmed | Unnamed: 21 | Notes | days_noa_to_consult | days_intake_to_submit | days_submit_to_finalize | days_irb | days_intake_to_dua_info | days_dua | days_total_process | irb_on_target | dua_on_target | total_on_target | meets_all_targets | is_completed | is_data_provided | year_quarter | risk_score | risk_level
Alexandra Kakadiaris | Research Fellowship Cohort 3 | 2024-09-26 | 2024-10-21 | 25 | 2024-10-31 | 10 |  | 2024-11-26 | 26 |  | 2024-12-09 | 74 | 2024-10-28 | 7 | 2024-12-06 | 2025-01-02 | 98 | 2025-01-23 | 119 | 2025-01-23 | 119 |  | 25 | 10 | 26 | 74 | 7 | 98 | 119 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 2024-Q4 | 4 | Medium
Andrew Nguyen | Research Fellowship Cohort 3 | 2024-09-26 | 2024-10-17 | 21 | 2024-10-22 | 5 |  | 2024-12-23 | 62 |  | 2025-02-15 | 142 | 2024-11-22 | 36 | 2024-12-24 | 2025-03-20 | 175 | 2025-03-25 | 180 | 2025-04-01 | 187 | -Requirement of GPUs | 21 | 5 | 62 | 142 | 36 | 175 | 180 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 2024-Q4 | 4 | Medium
Howard Prioleau | Research Fellowship Cohort 3 | 2024-09-26 | 2024-10-21 | 25 | 2024-10-28 | 7 |  | 2025-01-14 | 78 |  | 2025-03-23 | 178 |  |  | 2025-01-21 | 2025-05-08 | 224 | 2025-05-09 | 225 |  |  | Delays in finalizing data request | 25 | 7 | 78 | 178 |  | 224 | 225 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | 2024-Q4 | 7 | High
Korin Reid | Research Fellowship Cohort 3 | 2024-09-26 | 2024-10-31 | 35 | 2024-11-21 | 21 | 2024-12-12 | 2025-01-14 | 54 |  | 2025-03-05 | 160 | 2024-10-11 | -20 | 2025-01-21 | 2025-02-04 | 131 | 2025-03-19 | 174 | 2025-03-27 | 182 | Delays in finalizing data request | 35 | 21 | 54 | 160 | -20 | 131 | 174 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 2024-Q4 | 6 | High
Ling Zhang | Research Fellowship Cohort 3 | 2024-09-26 | 2024-11-04 | 39 | 2024-11-12 | 8 | 2024-12-09 | 2024-12-10 | 28 |  | 2025-01-06 | 102 | 2024-10-15 | -20 | 2024-12-17 | 2025-02-04 | 131 | 2025-02-10 | 137 | 2025-02-13 | 140 |  | 39 | 8 | 28 | 102 | -20 | 131 | 137 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 2024-Q4 | 5 | High
Lucretia Williams | Research Fellowship Cohort 3 | 2024-09-26 | 2024-10-15 | 19 | 2024-10-23 | 8 | 2024-11-18 | 2024-11-20 | 28 |  | 2025-02-03 | 130 | 2024-10-30 | 15 | 2024-12-06 | 2025-04-02 | 188 | 2025-04-03 | 189 | 2025-04-10 | 196 |  | 19 | 8 | 28 | 130 | 15 | 188 | 189 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 2024-Q4 | 7 | High
Pegah Ahadian | Research Fellowship Cohort 3 | 2024-09-26 | 2024-11-05 | 40 | 2024-11-10 | 5 |  | 2024-11-29 | 19 |  | 2024-12-11 | 76 | 2024-12-04 | 29 | 2024-12-09 | 2024-12-23 | 88 | 2025-01-16 | 112 | 2025-01-23 | 119 |  | 40 | 5 | 19 | 76 | 29 | 88 | 112 | FALSE | TRUE | FALSE | FALSE | TRUE | TRUE | 2024-Q4 | 3 | Medium
Xuan Wang | Research Fellowship Cohort 3 | 2024-09-26 | 2024-10-16 | 20 | 2024-10-18 | 2 |  | 2024-11-26 | 39 |  | 2024-11-08 | 43 | 2024-10-11 | -5 | 2024-12-06 | 2025-01-30 | 126 | 2025-01-30 | 126 | 2025-02-19 | 146 |  | 20 | 2 | 39 | 43 | -5 | 126 | 126 | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | 2024-Q4 | 2 | Low
Sohail Vaghari | CLINAQ Cohort 1 | 2024-10-15 | 2024-11-05 | 21 | 2024-11-18 | 13 |  | 2025-03-14 | 116 |  | 2025-02-24 | 132 | 2024-12-23 |  | 2025-03-17 | 2025-04-04 | 171 | 2025-04-02 | 169 | 2025-04-10 | 177 | Requirement of EchoNet Deep Learning Model- Available via GitHub which is not permissable on AADB Infrastructure due to security measures | 21 | 13 | 116 | 132 |  | 171 | 169 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 2024-Q4 | 4 | Medium
Candice Adams-Mitchell | CLINAQ Cohort 1 | 2024-10-15 | 2024-11-14 | 30 | 2024-11-25 | 11 |  | 2025-01-16 | 52 |  | 2025-03-05 | 141 |  |  | 2025-02-07 | 2025-02-27 | 135 | 2025-03-06 | 142 | 2025-03-25 | 161 |  | 30 | 11 | 52 | 141 |  | 135 | 142 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 2024-Q4 | 4 | Medium
Adebola Sulaiman | CLINAQ Cohort 1 | 2024-10-15 | 2024-10-29 | 14 | 2024-12-03 | 35 | 2024-11-26 |  |  |  | 2025-03-27 | 163 | [10 empty] | 14 | 35 |  | 163 |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2024-Q4 | 3 | Medium
Asha Imanuelle | CLINAQ Cohort 1 | 2024-10-15 | 2024-11-18 | 34 | 2024-12-01 | 13 |  | 2025-02-12 | 73 |  | 2025-03-14 | 150 | 2025-01-30 |  | 2025-02-17 | 2025-03-17 | 153 | 2025-03-28 | 164 | 2025-04-15 | 182 |  | 34 | 13 | 73 | 150 |  | 153 | 164 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 2024-Q4 | 5 | High
Yanmin Gong | CDP | 2023-09-23 | 2024-09-10 | 353 | 2024-11-21 | 72 | 2024-12-10 | 2024-12-23 | 104 |  | 2025-01-31 | 143 | 2024-12-19 |  | 2025-01-07 | 2025-02-27 | 170 | 2025-03-07 | 178 | 2025-03-20 | 191 |  | 353 | 72 | 104 | 143 |  | 170 | 178 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 2024-Q3 | 6 | High
Ying Yin/Sean Vasaitis | CDP | 2023-09-23 | 2024-09-10 | 353 | 2024-12-11 | 92 |  | 2025-03-12 | 183 |  | 2024-09-30 | 20 |  |  |  | 2025-04-09 | 211 | 2025-04-16 | 218 | 2025-04-17 | 219 |  | 353 | 92 | 183 | 20 |  | 211 | 218 | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | 2024-Q3 | 7 | High
Debi Alexander | CDP | 2024-10-02 | 2025-01-09 | 99 | 2025-03-12 | 62 | [16 empty] | 99 | 62 | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2025-Q1 | 2 | Low
Eva Sterling/ Xinyan Zhang | Hub Pilot Program | 2024-09-16 | 2024-11-13 | 58 | 2024-11-13 | 0 |  | 2024-12-06 | 23 |  | 2025-02-28 | 165 | 2025-02-19 | 98 |  | 2025-04-03 | 199 | 2025-04-03 | 199 | 2025-04-11 | 207 |  | 58 | 0 | 23 | 165 | 98 | 199 | 199 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 2024-Q4 | 8 | High
Uduak George | PAIR | 2024-10-01 | 2024-12-12 | 72 | 2024-12-17 | 5 |  | 2025-01-09 | 23 |  | 2025-01-10 | 101 | 2024-12-16 |  | 2025-01-21 | 2025-01-29 | 120 | 2025-02-21 | 143 | 2025-03-14 | 164 |  | 72 | 5 | 23 | 101 |  | 120 | 143 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | 2024-Q4 | 5 | High

## Recommendations
Priority | Recommendation
1 | Accelerate initial consultation scheduling: Currently 74 days avg (target: 30 days). Increase staff capacity.
2 | Address Submission to Finalization delays: Reduce from 61 to 30 days through process optimization.
3 | Streamline IRB process: Currently 120 days avg (target: 60 days). Consider expedited review procedures.
4 | Focus improvement efforts on CDP: Only 0% meeting all targets. Conduct detailed process review.
5 | Focus improvement efforts on CLINAQ Cohort 1: Only 0% meeting all targets. Conduct detailed process review.